## Sheet1
ID | Name | Start | Predecessors | Summary | Outline_Number | Outline_Level | Percent_Complete | Text1_Unitname | Number1 | Actual_Start | Actual_Finish | Duration | Constraint_Type | Constraint_Date | Task_Mode | Actual_Duration
1 | CONSTRUCTION |  |  | 1 | 1 | 0 | 0.000000 |  | 791199 |  |  | 0 |  |  | As Soon As Possible | 0
2 | M 25 |  |  | 1 | 2 | 1 | 0.000000 |  | 794433 |  |  | 4 |  |  | As Soon As Possible | 0
3 | M 25 Column Concrete M 25 | 21-02-2024 |  | 0 | 3 | 2 | 0.100000 |  | 794434 | 21-02-2024 |  | 4 | Must Start On | 17-06-2023 | As Soon As Possible | -45341
4 | M 25 Column Concrete M 25 | 21-02-2024 |  | 0 | 3 | 2 | 0.100000 |  | 796684 | 21-02-2024 |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | -45341
5 | CONSTRUCTION BBM 4" | 21-02-2024 |  | 0 | 3 | 2 | 0.100000 |  | 791200 | 21-02-2024 |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | -45341
6 | CONSTRUCTION Column Concrete M 25 | 21-02-2024 |  | 0 | 3 | 2 | 0.100000 |  | 791302 | 21-02-2024 |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | -45341
7 | M 25 Column Concrete M 25 | 04-04-2023 |  | 0 | 3 | 2 | 0.000000 |  | 816821 |  |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | 0
8 | FIRST FLOOR |  |  | 1 | 2 | 1 | 0.000000 |  | 816713 |  |  | 0 |  |  | As Soon As Possible | 0
9 | FIRST FLOOR Column Concrete M 25 | 02-03-2024 |  | 0 | 3 | 2 | 1.000000 |  | 816714 | 02-03-2024 |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | -45351
10 | SECOND FLOOR |  |  | 1 | 2 | 1 | 0.000000 |  | 816717 |  |  | 0 |  |  | As Soon As Possible | 0
11 | SECOND FLOOR Column Concrete M 25 | 04-04-2023 |  | 0 | 3 | 2 | 0.000000 |  | 816718 |  |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | 0
12 | SECOND FLOOR Column Concrete M 25 | 04-04-2023 |  | 0 | 3 | 2 | 0.000000 |  | 816812 |  |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | 0
13 | THIRD FLOOR |  |  | 1 | 2 | 1 | 0.000000 |  | 818050 |  |  | 0 |  |  | As Soon As Possible | 0
14 | THIRD FLOOR Column Concrete M 25 | 04-04-2023 |  | 0 | 3 | 2 | 0.000000 |  | 818051 |  |  | 0 | Must Start On | 04-04-2023 | As Soon As Possible | 0