## Sheet1
GREEN HIVE PLUS (A2 BUILDING ) - DAILY PROGRESS REPORT
Date :-19.09.2022
19.09.2022
sr.no | Activity | location | Therotical qty | Unit | WORK DESCRIPTION | Name | MATERIAL QTY | Unit | Today Material qty
1 | RCC WORK | A2 BUILDING
A | CARPENTER |  | 5 | NOS | 1) Above 9th Slab Column Shuttering Work | RMC | 60 | Cu.m | 10
B | FITTER |  | 13 | NOS | 2) Above 9th Slab Column Casting Work
C | M/C |  | 9 | NOS | 3) Above 9th Slab Column Binding Work
D | F/C |  | 2 | NOS
2 | ELECTRIC WORK | A2 BUILDING | 0 | NOS
3 | DEPARTMENT LABOURS
A | M/C |  | 1 | NOS | 1) Above 9th Slab Column Curing work
B | F/C |  | 0 | NO | 2)Cube Casting work
3) Parking Cleaning Work
4) Pump on/off Work