## 1Quality Check63731914954033254
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| From 01 Jun 2020 To 05 Aug 2020 | From 01 Jun 2020 To 05 Aug 2020 | From 01 Jun 2020 To 05 Aug 2020 | From 01 Jun 2020 To 05 Aug 2020 | From 01 Jun 2020 To 05 Aug 2020 | From 01 Jun 2020 To 05 Aug 2020 | From 01 Jun 2020 To 05 Aug 2020
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
FLAT NO. 101 Gypsum Plaster | 10.Corner Right angle checked | Corner Right angle checked | CON/515 | Engineer - Elite | 2020-07-17 | Approved | Ok
FLAT NO. 101 Gypsum Plaster | 11.Electrical consealed box cutting in shape after application | Electrical consealed box cutting in shape after application | CON/515 | Engineer - Elite | 2020-07-17 | Approved | ok
FLAT NO. 101 Gypsum Plaster | 12.Cleaning |  |  | Engineer - Elite | 2020-07-17 | Rejected | NRequired cleaning againe properly
FLAT NO. 101 Gypsum Plaster | 3.Use of bonding agent before applying gypsum | Use of bonding agent before applying gypsum | CON/515 | Engineer - Elite | 2020-07-17 | Approved | NA
FLAT NO. 101 Gypsum Plaster | 4.Door/ Window frame plumb checked | Door/ Window frame plumb checked | CON/515 | Engineer - Elite | 2020-07-17 | Approved | Ok
FLAT NO. 101 Gypsum Plaster | 6.Check the mix proportion. It is workable. | Check the mix proportion. It is workable. | CON/515 | Engineer - Elite | 2020-07-17 | Approved | 1:1.25
FLAT NO. 101 Gypsum Plaster | 7.Thickness,line & plumb checked | Thickness,line & plumb checked | CON/515 | Engineer - Elite | 2020-07-17 | Approved | 12mm