## 1Quality Check63732237130796885
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 8 Records 1 To 8 | Total Records: 8 Records 1 To 8 | Total Records: 8 Records 1 To 8 | Total Records: 8 Records 1 To 8 | Total Records: 8 Records 1 To 8 | Total Records: 8 Records 1 To 8 | Total Records: 8 Records 1 To 8
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
102 MASTER TOILET - Cu. Basecoat Waterproof | 01. Removal of all debris & cleaning | Removal of all debris ( Cleaning of surface with wire brush ) |  | Engineer - Elite | 2020-08-05 | Approved | DONE
102 MASTER TOILET - Cu. Basecoat Waterproof | 02. Slab chipping & loose surface clean | Slab chipping & loose surface clean |  | Engineer - Elite | 2020-08-05 | Approved | CORNER CHPPING, LOOSE CONCRETE REMOVED,
102 MASTER TOILET - Cu. Basecoat Waterproof | 03. Making of holes required for outlets | Making of holes required for all types of outlets. |  | Engineer - Elite | 2020-08-05 | Approved | AS PER PLUMBING DRAWING
102 MASTER TOILET - Cu. Basecoat Waterproof | 04. Availability of material for bascoat | Availability of material for bascoat i.e chemical,cement,river sand,etc. |  | Engineer - Elite | 2020-08-05 | Approved | RIVER SAND , PPC CEMENT BASF SBR CHEMICAL COMPOUND
102 MASTER TOILET - Cu. Basecoat Waterproof | 05. Check for mix proportion | Check for mix proportion - 1:4 |  | Engineer - Elite | 2020-08-05 | Approved | C:M 1:6
102 MASTER TOILET - Cu. Basecoat Waterproof | 06. Checking of chemical brushing. | Checking of chemical brushing of basecoat
102 MASTER TOILET - Cu. Basecoat Waterproof | 07. Checking of executed basecoat work | Checking of executed basecoat work - Required 300 mm above slab level
102 MASTER TOILET - Cu. Basecoat Waterproof | 08. Checking of ponding/curing | Checking of ponding/curing for basecoat minimum 5 days