## 1Quality Check63735795637453710
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 10 Records 1 To 10 | Total Records: 10 Records 1 To 10 | Total Records: 10 Records 1 To 10 | Total Records: 10 Records 1 To 10 | Total Records: 10 Records 1 To 10 | Total Records: 10 Records 1 To 10 | Total Records: 10 Records 1 To 10
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 10. Check for plumb/ line/ level of masonary | Check for plumb/ line/ level of masonary | CON/513 | Engineer - Elite | 2020-08-25 | Approved | found ok
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 11. Check for plumb/ line/ level of doors, windows |  |  | Engineer - Elite | 2020-08-25 | Approved | as per general practice all line and plumb checking found ok
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 2. Line out rechecked | Line out rechecked | CON/513 | Engineer - Elite | 2020-08-25 | Approved | yes as per working drawing checking the main diagonal of the outer line checking out to out dimention and its digona found ok
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 3. Cleaning work area off loose material/ concrete | Cleaning work area off loose material/ concrete | CON/513 | Engineer - Elite | 2020-08-25 | Approved | before stacking of aac block all floor cleaning of loose concrete mortor on throughout floor found ok
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 4. Hacking of concrete complete | Hacking of concrete complete | CON/513 | Engineer - Elite | 2020-08-25 | Approved | all beam bottom are check to proper hacking of tacha work found ok
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 4.Fill gaps with non shrink material | "RCC Beam,Column & masonry gaps shall be filled with non shrink material & pebbles" | CON/513 | Engineer - Elite | 2020-08-25 | Approved | internal side all gap are fill up using emax mortor of block chemical joint
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 6. Check for dimensional accuracy (Room size and diagonals etc) | Check for dimensional accuracy (Room size and diagonals etc) | CON/513 | Engineer - Elite | 2020-08-25 | Approved | all room size as per working drawing found ok
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 7. Check for door / window opening sizes | Check for door / window opening sizes | CON/513 | Engineer - Elite | 2020-08-25 | Approved | as per working drawing
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 8. Provision for patli/ Sill/ Holdfast | Provision for patli/ Sill/ Holdfast | CON/513 | Engineer - Elite | 2020-08-25 | Approved | patli is casting but not applicable of hold fast
5thFLOOR BLOCK WORK AAC Block Masonry 150mm - Sft. | 9. DPC course complete as per Line out | DPC course complete as per Line out-checked | CON/513 | Engineer - Elite | 2020-08-25 | Approved | yes