## 1Quality Check63735797753023202
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 60 Records 1 To 60 | Total Records: 60 Records 1 To 60 | Total Records: 60 Records 1 To 60 | Total Records: 60 Records 1 To 60 | Total Records: 60 Records 1 To 60 | Total Records: 60 Records 1 To 60 | Total Records: 60 Records 1 To 60
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
402 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 01. Check basecoat waterproof completed | 1.Check basecoat waterproof is complete
402 MASTER TOILET - Cu. Brick Bat W/P (Toilet/Terrace) | 01. Check basecoat waterproof completed | 1.Check basecoat waterproof is complete
402 DRY BALCONY - Cu Brick Bat W/P (Toilet/Terrace) | 01. Check basecoat waterproof completed | 1.Check basecoat waterproof is complete
402 TERRACE - Cu. - Brick Bat W/P (Toilet/Terrace) | 01. Check basecoat waterproof completed | 1.Check basecoat waterproof is complete
402 TERRACE - Cu. - Basecoat Waterproof | 01. Removal of all debris & cleaning | Removal of all debris ( Cleaning of surface with wire brush )
402 DRY BALCONY - Cu Basecoat Waterproof | 01. Removal of all debris & cleaning | Removal of all debris ( Cleaning of surface with wire brush )
402 COMMON TOILET Basecoat Waterproof | 01. Removal of all debris & cleaning | Removal of all debris ( Cleaning of surface with wire brush )
402 MASTER TOILET - Cu. Basecoat Waterproof | 01. Removal of all debris & cleaning | Removal of all debris ( Cleaning of surface with wire brush )
402 MASTER TOILET - Cu. Brick Bat W/P (Toilet/Terrace) | 02. Cleaning of basecoat surface | Cleaning of basecoat surface
402 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 02. Cleaning of basecoat surface | Cleaning of basecoat surface
402 TERRACE - Cu. - Brick Bat W/P (Toilet/Terrace) | 02. Cleaning of basecoat surface | Cleaning of basecoat surface
402 DRY BALCONY - Cu Brick Bat W/P (Toilet/Terrace) | 02. Cleaning of basecoat surface | Cleaning of basecoat surface
402 TERRACE - Cu. - Basecoat Waterproof | 02. Slab chipping & loose surface clean | Slab chipping & loose surface clean
402 DRY BALCONY - Cu Basecoat Waterproof | 02. Slab chipping & loose surface clean | Slab chipping & loose surface clean
402 MASTER TOILET - Cu. Basecoat Waterproof | 02. Slab chipping & loose surface clean | Slab chipping & loose surface clean
402 COMMON TOILET Basecoat Waterproof | 02. Slab chipping & loose surface clean | Slab chipping & loose surface clean
402 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 03. Check of floor piping done | Fixing of plumbing and drainage pipes and other assesories as per drawing
402 MASTER TOILET - Cu. Brick Bat W/P (Toilet/Terrace) | 03. Check of floor piping done | Fixing of plumbing and drainage pipes and other assesories as per drawing
402 DRY BALCONY - Cu Brick Bat W/P (Toilet/Terrace) | 03. Check of floor piping done | Fixing of plumbing and drainage pipes and other assesories as per drawing
402 TERRACE - Cu. - Brick Bat W/P (Toilet/Terrace) | 03. Check of floor piping done | Fixing of plumbing and drainage pipes and other assesories as per drawing
402 TERRACE - Cu. - Basecoat Waterproof | 03. Making of holes required for outlets | Making of holes required for all types of outlets.
402 DRY BALCONY - Cu Basecoat Waterproof | 03. Making of holes required for outlets | Making of holes required for all types of outlets.
402 COMMON TOILET Basecoat Waterproof | 03. Making of holes required for outlets | Making of holes required for all types of outlets.
402 MASTER TOILET - Cu. Basecoat Waterproof | 03. Making of holes required for outlets | Making of holes required for all types of outlets.
402 MASTER TOILET - Cu. Basecoat Waterproof | 04. Availability of material for bascoat | Availability of material for bascoat i.e chemical,cement,river sand,etc.
402 COMMON TOILET Basecoat Waterproof | 04. Availability of material for bascoat | Availability of material for bascoat i.e chemical,cement,river sand,etc.
402 DRY BALCONY - Cu Basecoat Waterproof | 04. Availability of material for bascoat | Availability of material for bascoat i.e chemical,cement,river sand,etc.
402 TERRACE - Cu. - Basecoat Waterproof | 04. Availability of material for bascoat | Availability of material for bascoat i.e chemical,cement,river sand,etc.
402 TERRACE - Cu. - Brick Bat W/P (Toilet/Terrace) | 04.Availability of material for brickbat | Availability of material for bascoat i.e cement,river sand,etc.
402 DRY BALCONY - Cu Brick Bat W/P (Toilet/Terrace) | 04.Availability of material for brickbat | Availability of material for bascoat i.e cement,river sand,etc.
402 MASTER TOILET - Cu. Brick Bat W/P (Toilet/Terrace) | 04.Availability of material for brickbat | Availability of material for bascoat i.e cement,river sand,etc.
402 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 04.Availability of material for brickbat | Availability of material for bascoat i.e cement,river sand,etc.
402 DRY BALCONY - Cu Basecoat Waterproof | 05. Check for mix proportion | Check for mix proportion - 1:4
402 COMMON TOILET Basecoat Waterproof | 05. Check for mix proportion | Check for mix proportion - 1:4
402 MASTER TOILET - Cu. Basecoat Waterproof | 05. Check for mix proportion | Check for mix proportion - 1:4
402 TERRACE - Cu. - Basecoat Waterproof | 05. Check for mix proportion | Check for mix proportion - 1:4
402 DRY BALCONY - Cu Brick Bat W/P (Toilet/Terrace) | 05. Checking for mix proportion | Check for mix proportion in 1:4
402 TERRACE - Cu. - Brick Bat W/P (Toilet/Terrace) | 05. Checking for mix proportion | Check for mix proportion in 1:4
402 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 05. Checking for mix proportion | Check for mix proportion in 1:4
402 MASTER TOILET - Cu. Brick Bat W/P (Toilet/Terrace) | 05. Checking for mix proportion | Check for mix proportion in 1:4
402 DRY BALCONY - Cu Basecoat Waterproof | 06. Checking of chemical brushing. | Checking of chemical brushing of basecoat
402 MASTER TOILET - Cu. Basecoat Waterproof | 06. Checking of chemical brushing. | Checking of chemical brushing of basecoat
402 COMMON TOILET Basecoat Waterproof | 06. Checking of chemical brushing. | Checking of chemical brushing of basecoat
402 TERRACE - Cu. - Basecoat Waterproof | 06. Checking of chemical brushing. | Checking of chemical brushing of basecoat
402 TERRACE - Cu. - Brick Bat W/P (Toilet/Terrace) | 06. Checking of executed brickbat work | Checking of executed brickbat work
402 DRY BALCONY - Cu Brick Bat W/P (Toilet/Terrace) | 06. Checking of executed brickbat work | Checking of executed brickbat work
402 MASTER TOILET - Cu. Brick Bat W/P (Toilet/Terrace) | 06. Checking of executed brickbat work | Checking of executed brickbat work
402 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 06. Checking of executed brickbat work | Checking of executed brickbat work
402 DRY BALCONY - Cu Basecoat Waterproof | 07. Checking of executed basecoat work | Checking of executed basecoat work - Required 300 mm above slab level
402 COMMON TOILET Basecoat Waterproof | 07. Checking of executed basecoat work | Checking of executed basecoat work - Required 300 mm above slab level |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 MASTER TOILET - Cu. Basecoat Waterproof | 07. Checking of executed basecoat work | Checking of executed basecoat work - Required 300 mm above slab level |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 TERRACE - Cu. - Basecoat Waterproof | 07. Checking of executed basecoat work | Checking of executed basecoat work - Required 300 mm above slab level |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 DRY BALCONY - Cu Brick Bat W/P (Toilet/Terrace) | 07. Checking of ponding/curing | Checking of ponding/curing minimum 3 days |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 TERRACE - Cu. - Brick Bat W/P (Toilet/Terrace) | 07. Checking of ponding/curing | Checking of ponding/curing minimum 3 days |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 COMMON TOILET Brick Bat W/P (Toilet/Terrace) | 07. Checking of ponding/curing | Checking of ponding/curing minimum 3 days |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 MASTER TOILET - Cu. Brick Bat W/P (Toilet/Terrace) | 07. Checking of ponding/curing | Checking of ponding/curing minimum 3 days |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 DRY BALCONY - Cu Basecoat Waterproof | 08. Checking of ponding/curing | Checking of ponding/curing for basecoat minimum 5 days |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok and fill up water found ok
402 MASTER TOILET - Cu. Basecoat Waterproof | 08. Checking of ponding/curing | Checking of ponding/curing for basecoat minimum 5 days |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok
402 COMMON TOILET Basecoat Waterproof | 08. Checking of ponding/curing | Checking of ponding/curing for basecoat minimum 5 days |  | Engineer - Elite | 2020-09-15 | Approved | removing all dust to wash using water and apply wp basf chemical compound n found ok
402 TERRACE - Cu. - Basecoat Waterproof | 08. Checking of ponding/curing | Checking of ponding/curing for basecoat minimum 5 days |  | Engineer - Elite | 2020-09-15 | Approved | chiseling hammer use and removing all debris rabid material removing all dust to wash using water and apply wp basf chemical compound n found ok