## 1Quality Check63736130208655876
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
FLAT NO. 603 Tar Plaster - Sft. | 1. Availability of material for plastering
FLAT NO. 603 Tar Plaster - Sft. | 1. Check For Mix proportion for plastering | Check For Mix proportion | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 11. Plaster done as per skirting, toilet,washbasin & kitchen dado level | Plaster done as per skirting, toilet,washbasin & kitchen dado level | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 12. Application of neeru | Application of neeru | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 13. Cleaning & Finishing of electrical point , Fan hook, window & door | Cleaning & Finishing of electrical point , Fan hook, window & door | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 2. Curing For Plastering | Curing For Plastering | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 3. Filling of gap between beam and masonary wall | Filling of gap between beam and masonary wall | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 4. Application of chemical (Hack aid etc.) to concrete surface done | Application of chemical (Hack aid etc.) to concrete surface done | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 4. Hacking of concrete and racking of joints complete | Hacking of concrete and racking of joints complete | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 5. Provision of chicken mesh | Provision of chicken mesh | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 6. Consumption of mortor within 1/2 hour after addition of water | Consumption of mortor within 1/2 hour after addition of water | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 6. Prewetting of plaster surface | Prewetting of plaster surface | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 7. Thickness, Line And Plumb Checked | Thickness, Line And Plumb Checked | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 8. Corner Right Angles Checked | Corner Right Angles Checked | CON/516
FLAT NO. 603 Tar Plaster - Sft. | 8. Provision of plaster screeds / Thiyas | Provision of plaster screeds / Thiyas | CON/516 | Engineer - Elite | 2020-09-19 | Approved | APPLY THE BOTTOM THIYAS OF ALL WALL NOMINAL THIKNESS 12MM DONE
FLAT NO. 603 Tar Plaster - Sft. | 9. Level of sill & soffit and plumb , right angle of jambs checked | Level of sill & soffit and plumb , right angle of jambs checked | CON/516 | Engineer - Elite | 2020-09-19 | Approved | CHECKING LEVEL FOR DOOR, LINTEL JAMS SEAL,SOFIT ALSO RIGHT ANGLE FOR EACH CORNER OF KITCHEN ROOM, DRY BALCONY COMM.TOILET, MAST. TOILET FOUND SOME OF KACH DHAR OUT TO REMAINTANE IT