## 1Quality Check63736131977398809
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16 | Total Records: 16 Records 1 To 16
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 1. Availability of material for plastering |  |  | Engineer - Elite | 2020-09-19 | Approved | YES
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 1. Check For Mix proportion for plastering | Check For Mix proportion | CON/516 | Engineer - Elite | 2020-09-19 | Approved | ACC READY MIX PLASTER MORTAR 1:4 PROPORTION CHECKED FOUND OK
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 11. Plaster done as per skirting, toilet,washbasin & kitchen dado level | Plaster done as per skirting, toilet,washbasin & kitchen dado level | CON/516 | Engineer - Elite | 2020-09-19 | Approved | DONE
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 12. Application of neeru | Application of neeru | CON/516 | Engineer - Elite | 2020-09-19 | Approved | ONLY CEILING OF SLAB PORTION APPLY MOR CHAP SUNLA DONE
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 13. Cleaning & Finishing of electrical point , Fan hook, window & door | Cleaning & Finishing of electrical point , Fan hook, window & door | CON/516 | Engineer - Elite | 2020-09-19 | Approved | CLEANING IS DONE ONLY DAY WORK AREA IN PLASTER PORTION THROU GH OUT FLAT NOT PROPERLY CLEAN
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 2. Curing For Plastering | Curing For Plastering | CON/516 | Engineer - Elite | 2020-09-19 | Approved | NEXT DAY START THE PLASTER SURFACES
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 3. Filling of gap between beam and masonary wall | Filling of gap between beam and masonary wall | CON/516 | Engineer - Elite | 2020-09-19 | Approved | internal side emax block joint mortar filling gap is done
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 4. Application of chemical (Hack aid etc.) to concrete surface done | Application of chemical (Hack aid etc.) to concrete surface done | CON/516 | Engineer - Elite | 2020-09-19 | Approved | not apply
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 4. Hacking of concrete and racking of joints complete | Hacking of concrete and racking of joints complete | CON/516 | Engineer - Elite | 2020-09-19 | Approved | hacking of rcc memeber is done racking of aac block joint not applicable
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 5. Provision of chicken mesh | Provision of chicken mesh | CON/516 | Engineer - Elite | 2020-09-19 | Approved | Done only plane portion of composit member rcc and aac block joint portion only
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 6. Consumption of mortor within 1/2 hour after addition of water | Consumption of mortor within 1/2 hour after addition of water | CON/516 | Engineer - Elite | 2020-09-19 | Approved | None add to water rappiedly in mortar
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 6. Prewetting of plaster surface | Prewetting of plaster surface | CON/516 | Engineer - Elite | 2020-09-19 | Approved | Done
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 7. Thickness, Line And Plumb Checked | Thickness, Line And Plumb Checked | CON/516 | Engineer - Elite | 2020-09-19 | Approved | 15mm, line plum bottom patti checked found ok
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 8. Corner Right Angles Checked | Corner Right Angles Checked | CON/516 | Engineer - Elite | 2020-09-19 | Approved | Done
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 8. Provision of plaster screeds / Thiyas | Provision of plaster screeds / Thiyas | CON/516 | Engineer - Elite | 2020-09-19 | Approved | Done
FLAT NO. 601 Tar Plaster - Sft. - Sft. | 9. Level of sill & soffit and plumb , right angle of jambs checked | Level of sill & soffit and plumb , right angle of jambs checked | CON/516 | Engineer - Elite | 2020-09-19 | Approved | Done