## 1Quality Check63739585706021387
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7 | Total Records: 7 Records 1 To 7
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
5th FLOOR MS GRILL WORK M.S. Grill [M+L] - Sft. | 01.Study of drawings | Study of drawings | CON/526 | Engineer - Elite | 2020-10-29 | Approved | Ok
5th FLOOR MS GRILL WORK M.S. Grill [M+L] - Sft. | 02. Ensure mock up is approved. | Ensure mock up is approved. | CON/526 | Engineer - Elite | 2020-10-29 | Approved | Ok
5th FLOOR MS GRILL WORK M.S. Grill [M+L] - Sft. | 06. Check welding joints. | Check welding joints. | CON/526 | Engineer - Elite | 2020-10-29 | Approved | Ok
5th FLOOR MS GRILL WORK M.S. Grill [M+L] - Sft. | 08. Check straightness and bending. | Check straightness and bending. | CON/526 | Engineer - Elite | 2020-10-29 | Approved | Ok
5th FLOOR MS GRILL WORK M.S. Grill [M+L] - Sft. | 09. Check for fixing of grill, frame | Check for fixing of grill, frame | CON/526 | Engineer - Elite | 2020-10-29 | Approved | Ok
5th FLOOR MS GRILL WORK M.S. Grill [M+L] - Sft. | 10. Check plum line level | Check plum line level | CON/526 | Engineer - Elite | 2020-10-29 | Approved | Ok
5th FLOOR MS GRILL WORK M.S. Grill [M+L] - Sft. | 11.Check rigidity of structure after fixing. | Check rigidity of structure after fixing. | CON/526 | Engineer - Elite | 2020-10-29 | Approved | OK