## 1Requisition_Tracking-Summary63
| Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary
| From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020 | From Date : 14/10/2020 To date: 16/10/2020
| Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work | Material Category : Electrical Work
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24 | Total Records: 24 Records 1 to 24
Project | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | User_Name | Status | Remark
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15694 | 2020-10-14 12:00 | 2020-10-14 12:00 | 85 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15695 | 2020-10-14 12:00 | 2020-10-14 12:00 | 12 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15696 | 2020-10-14 12:00 | 2020-10-14 12:00 | 10 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15697 | 2020-10-14 12:00 | 2020-10-14 12:00 | 10 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15698 | 2020-10-14 12:00 | 2020-10-14 12:00 | 10 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15699 | 2020-10-14 12:00 | 2020-10-14 12:00 | 10 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15700 | 2020-10-14 12:00 | 2020-10-14 12:00 | 3 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15701 | 2020-10-14 12:00 | 2020-10-14 12:00 | 3 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15702 | 2020-10-14 12:00 | 2020-10-14 12:00 | 3 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | 25 MM PVC DEEP JUNCTION BOX 4 WAY | Nos | 15703 | 2020-10-14 12:00 | 2020-10-14 12:00 | 120 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC CONDUIT PIPE 25MM | Nos | 15704 | 2020-10-14 12:00 | 2020-10-14 12:00 | 150 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15767 | 2020-10-16 12:00 | 2020-10-16 12:00 | 225 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15768 | 2020-10-16 12:00 | 2020-10-16 12:00 | 151 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15769 | 2020-10-16 12:00 | 2020-10-16 12:00 | 225 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15770 | 2020-10-16 12:00 | 2020-10-16 12:00 | 433 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15771 | 2020-10-16 12:00 | 2020-10-16 12:00 | 433 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15772 | 2020-10-16 12:00 | 2020-10-16 12:00 | 433 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15773 | 2020-10-16 12:00 | 2020-10-16 12:00 | 600 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC BEND 25MM | Nos | 15774 | 2020-10-16 12:00 | 2020-10-16 12:00 | 355 | 0 | 0 | Purchase1 | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15777 | 2020-10-16 12:00 | 2020-10-16 12:00 | 101 | 0 | 0 | Estimation | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15778 | 2020-10-16 12:00 | 2020-10-16 12:00 | 433 | 0 | 0 | Estimation | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15779 | 2020-10-16 12:00 | 2020-10-16 12:00 | 433 | 0 | 0 | Estimation | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15780 | 2020-10-16 12:00 | 2020-10-16 12:00 | 433 | 0 | 0 | Estimation | Unapproved
GOODWILL FABIAN | PVC COUPLER 25MM | Nos | 15781 | 2020-10-16 12:00 | 2020-10-16 12:00 | 600 | 0 | 0 | Estimation | Unapproved