## Sheet1
ABL | List of queries
Sr.No. | Particular | Pranav Commets dt. 02/07/2019 | Kanix Remark
Engineering/Tender/Purchase Module
1 | Bank details in suppliers creation (vendor master) | After Go live | Customization Is required to be done here. Pls send confirmation so I can shere detail idea over it.
2 | Configuration of mail Details | SMTP will be provided by pankaj | Done. Only need to configure alert which I will do after coming there.
3 | Enquiry details with attachment. | After Go live | Shown In tender module. One can attach Enquiry details with enquiry in tender module Inward enquiry option.
4 | Quotation attachment | After Go live | Customization Is required to be done here. Pls send confirmation so I an shere detail idea over it.
5 | PO Format – (Format sent to Pranav) | with in 7 days | Done And deployed on your server pls check and confirm
6 | WO Format – (Format sent to Pranav) | with in 7 days | Done And deployed on your server pls check and confirm
7 | Jurisdiction header to be added in WO and PO | with in 7 days | Pls arrange concall with person who is having details idea over this with Mr. Pranav. He will configure that.
8 | While generating RA Bill, MB to be shown in tender | immediate | Under Development will deployed soon.
9 | User level configuration for Dashboard | later 3 months | later after 3 months from Go Live
10 | Checklist provision to the client |  | Please shere a checklist format with us so that we can upload it in tender module
11 | Govt BOQ Excel Configuration enabling. | share the format - Pankaj | Please shere a format with Mr. Pranav
12 | Upload document tab not working – Tender module ( Conveyed to Pranav ) | immediate | Working now please check and confirm.
13 | Tender submission date Alert to be on | immediate | Under Development will deployed soon.
14 | Checklist tab not working – Tender module | immediate | Will be shown after Point No. 10 resolved.
15 | Pan Number to be mandatory in contractor registration | immediate | Under Development will deployed soon.
16 | Tender type – How to create new tender type | immediate | Please shere type of tender. We will add it.
18 | Change - Equipment library – Run cost – Operating cost |  | Not Possible to Remane Field. In report one can show you that. Please confirm.
19 | Custom Material Report – Amit and PD |  | Please shere a format.
20 | . Allow some user to do backdated requisition & GRN |  | Back dated entry - Allow all or allow non is possible.
21 | Quotation – Add attachment (reply from supplier) |  | Under Development will deployed soon.
22 | should be able to enter minimum lead time material wise – AL |  | Customization is required to trigger alert. Please send confirmation so i can shere idea.
23 | Maximum stock limit alert |  | Customization is required to trigger alert. Please send confirmation so i can shere idea.
24 | Purchase Control -AL |  | Customization is required to trigger alert. Please send confirmation so i can shere idea.
25 | Batch no. to be added in the GRN |  | One can use Challan Non field as Batch no field.
26 | Share SMTP details of email server to enable mail automation |  | RESOLVED.
27 | Simultaneous login – App and web |  | Not possible
28 | to be switched on amouting format – Proper commas in Indian Rs. Standards, decial off billing format to be updated as per our old billing software. |  | Needs forms details, wheres requires.
29 | Manual do not exit – workflow, dashboard, Admin tool, HR |  | Deployed on admin tool/help option please check and confirm.
30 | Process token – what is this |  | Menu for Workflow module To activate token process.
31 | Turn on comparision and stop alert between contractor and client billing quantities |  | NO such alert is activated. One can take out report to compare between client billing and contractor.
Pay roll & HR
1 | Weekly off - veriable project wise |  | Available
2 | Holiday - veriable project wise |  | Available
3 | Salary Advance as a loan deduct in EMI. We requir different tab salary advance for one time deduction |  | Available
4 | Investment declaration - upload documents |  | Available
5 | Format - Revised Form 16 |  | Available
6 | Subcontractor compliance tab - Head wise, contractor wise |  | Customization Is required to be done here. Pls send confirmation so I an shere detail idea over it.
7 | Project wise employees transfer |  | Need more understanding
8 | outdoor duty - programme |  | Need more understanding
9 | Leave application to be prepare in HR Module |  | Available
10 | Other deduction head is required with narration |  | Available
11 | Addition head is require with narration |  | Available
12 | Salary Structure - Entry should be manual instead of % |  | Available
13 | Employee master - if bank account starts from 0. The 0 should be displyed |  | Available
14 | RTGS - payment format should be print from the hr module |  | Are you expecting salary desbursement?
15 | Bulk salary format |  | Available
16 | Proffessional charges should be project wise, Abl should have the rights to change as per state law |  | Available employee wise
17 | MLWF (Maharashtra Labour welfare fund) designation wise and state wise |  | available
18 | Increment approval tab (authorised person name should be mandatory to display.) |  | Need more understanding
19 | manual attendence should enter |  | available
Accounts
1 | Balance sheet as pe schedule 6 with two year comparision |  | Customization Is required to be done here. Pls send confirmation so I an shere detail idea over it.
2 | GST Mismatch report - your representetive not explained properly |  | To show record GST amount mismatch in Voucher and GST Configurtion.
3 | Pendency report of imprest |  | Need more understanding
4 | payment advice generation as per our format |  | Need format
5 | Negative cash alert. Shift to next date if payment made in cash is greater thn 10000 |  | Check ledger browse negetive cash shows in different colour code.
6 | cash flow statement as per accounting standards |  | Need format
7 | Aging of creditors as per our requirement |  | Please check Outstanding report - Aging / Without Aging
8 | Depriciation as per company law - not explained by Highreise rep. |  | Available in seaprate Fixed Asset Module Desktop
9 | Sales of asset register not reported in P & M |  | Available in seaprate Fixed Asset Module Desktop
Plant & Machinery
1 | Book value of machine should be displayed in P & M Module |  | Depreciation cost is available in Asset details. Already explained during training.
2 | Breakdown report to be generated |  | pLease shere report format on mail
3 | Preventive maintenance with reference to the hours
4 | job card generated automatically |  | need more understanding
5 | Utilization report generated automatically |  | pLease shere report format on mail
6 | pendency report of requisition |  | need more understanding
7 | Machines availability report |  | Available in equipment availability calander shown during training.
8 | Driver master should be in P & M module instead of Engineering module
9 | Project wise Equipment DPR
10 | Equipment Profit & loss report
11 | details of disposal of Old Assets or sold assets
Bugs
1 | Server document path configuration pending |  | Done.
2 | Download brochure |  | Done.
3 | HR Menu not displyed while assign rights
4 | how to assign rights in P & M Module |  | In desktop version of admin tool as P&M module is desktop one.
5 | how to change user id |  | expire user and create user with its lic key. Change user id is not possible.