## Task_Table
ID | Task Name | Duration | Start | Finish | Predecessors | Resource Names
1 | MAHINDRA WORLD CITY, PUDUVOYAL- Program Schedule for GLSR | 165.67 days | Sat 2/16/19 | Fri 8/30/19
2 | Earth work excavation | 10 days | Sat 2/16/19 | Thu 2/28/19
3 | Compaction and testing | 4 days | Tue 3/05/19 | Sat 3/09/19 | 2
4 | PCC - Collection pit | 1 day | Sat 3/09/19 | Mon 3/11/19 | 3
5 | Raft - collection pit-rebar | 1 day | Tue 3/19/19 | Wed 3/20/19 | 4
6 | Raft - collection pit-shuttering | 1 day | Wed 3/20/19 | Thu 3/21/19 | 5
7 | Raft - collection pit-concrete | 1 day | Thu 3/21/19 | Fri 3/22/19 | 6
8 | wall up to base | 2 days | Fri 3/22/19 | Mon 3/25/19 | 7
9 | hard core layer | 2 days | Mon 3/25/19 | Wed 3/27/19 | 8
10 | PCC 1:4:8 | 2 days | Tue 4/09/19 | Thu 4/11/19 | 9
11 | reinforcement for raft | 10 days | Thu 4/11/19 | Tue 4/23/19 | 10
12 | shuttering for raft | 4 days | Tue 4/23/19 | Sat 4/27/19 | 11
13 | RCC Raft concrete | 2 days | Sat 4/27/19 | Tue 4/30/19 | 12
14 | RCC wall starter marking | 1 day | Tue 4/30/19 | Thu 5/02/19 | 13
15 | RCC wall startrer shuttering and concreting (outer wall) | 2 days | Thu 5/02/19 | Sat 5/04/19 | 14
16 | RCC wall startrer shuttering and concreting (inner wall) | 2 days | Sat 5/04/19 | Tue 5/07/19 | 15
17 | RCC wall upto 1.2 Rm- rebar | 2 days | Tue 5/07/19 | Thu 5/09/19 | 16
18 | RCC wall upto 1.2 Rm- shuttering | 3 days | Thu 5/09/19 | Mon 5/13/19 | 17
19 | RCC wall upto 1.2 Rm- concreting | 1 day | Mon 5/13/19 | Tue 5/14/19 | 18
20 | RCC wall upto 2.4 Rm-rebar | 2 days | Tue 5/14/19 | Thu 5/16/19 | 19
21 | RCC wall upto 2.4 Rm-shuttering | 4 days | Thu 5/16/19 | Tue 5/21/19 | 20
22 | RCC wall upto 2.4 Rm-concreting | 1 day | Tue 5/21/19 | Wed 5/22/19 | 21
23 | RCC wall upto 3.55 Rm-rebar | 2 days | Wed 5/22/19 | Fri 5/24/19 | 22
24 | RCC wall upto 3.55 Rm-shuttering | 4 days | Fri 5/24/19 | Wed 5/29/19 | 23
25 | RCC wall upto 3.55 Rm-concreting | 1 day | Wed 5/29/19 | Thu 5/30/19 | 24
26 | RCC wall upto 4.5Rm- rebar | 2 days | Thu 5/30/19 | Sat 6/01/19 | 25
27 | RCC wall upto 4.5 Rm- shuttering | 5 days | Sat 6/01/19 | Fri 6/07/19 | 26
28 | RCC wall upto 4.5 Rm- concreting | 1 day | Fri 6/07/19 | Sat 6/08/19 | 27
29 | RCC wall upto 1.2 Rm- rebar (Outer wall) | 2 days | Sat 6/08/19 | Tue 6/11/19 | 28
30 | RCC wall upto 1.2 Rm- shuttering | 3 days | Tue 6/11/19 | Fri 6/14/19 | 29
31 | RCC wall upto 1.2 Rm- concreting | 1 day | Fri 6/14/19 | Sat 6/15/19 | 30
32 | RCC wall upto 2.4 Rm-rebar | 2 days | Sat 6/15/19 | Tue 6/18/19 | 31
33 | RCC wall upto 2.4 Rm-shuttering | 3 days | Tue 6/18/19 | Fri 6/21/19 | 32
34 | RCC wall upto 2.4 Rm-concreting | 1 day | Fri 6/21/19 | Sat 6/22/19 | 33
35 | RCC wall upto 3.55 Rm-rebar | 2 days | Sat 6/22/19 | Tue 6/25/19 | 34
36 | RCC wall upto 3.55 Rm-shuttering | 3 days | Tue 6/25/19 | Fri 6/28/19 | 35
37 | RCC wall upto 3.55 Rm-concreting | 1 day | Fri 6/28/19 | Sat 6/29/19 | 36
38 | RCC wall upto 4.5Rm- rebar | 2 days | Sat 6/29/19 | Tue 7/02/19 | 37
39 | RCC wall upto 4.5 Rm- shuttering | 3 days | Tue 7/02/19 | Fri 7/05/19 | 38
40 | RCC wall upto 4.5 Rm- concreting | 1 day | Fri 7/05/19 | Sat 7/06/19 | 39
41 | doom slab shuttering | 15 days | Sat 7/06/19 | Wed 7/24/19 | 40
42 | doom slab reinforcement | 10 days | Wed 7/24/19 | Mon 8/05/19 | 41
43 | doom slab concrete | 1 day | Mon 8/05/19 | Tue 8/06/19 | 42
44 | deshuttering | 2 days | Tue 8/06/19 | Thu 8/08/19 | 43
45 | waterproofing inner | 3 days | Mon 8/12/19 | Fri 8/16/19 | 44FS+3 days
46 | wall plastering inner | 5 days | Fri 8/16/19 | Thu 8/22/19 | 45
47 | wall plastering outer | 7 days | Thu 8/22/19 | Fri 8/30/19 | 46
48 | grano flooring | 3 days | Thu 8/22/19 | Sun 8/25/19 | 46
49 | plinth protection | 1 day | Sun 8/25/19 | Mon 8/26/19
50 | cement painting out side | 1 day | Sun 8/25/19 | Mon 8/26/19
51 | MS hand railing | 5 days | Tue 8/20/19 | Sun 8/25/19
52 | MS grill and ladder | 5 days | Tue 8/20/19 | Sun 8/25/19
53 | CLEANING & HANDING OVER | 5 days | Sun 8/25/19 | Fri 8/30/19 | 52FS--1 days

## Resource_Table
ID | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code

## Assignment_Table
Uid | Task name | Resource name | Work | Duration