## Catchup schedule GLSR
Description | Finish Date
GLSR - 2500 cum (2500000 litre) | 2019-10-01
Outer Dia - 27.6 mtr
Inner Dia - 19 mtr
Total Height - 9 mtr
Area of Dome slab - 1195.963 sqm
| AS PER SCHEDULE |  |  | CATCH-UP SCHEDULE
GLSR | Start Date | Finish Date | Duration | Start Date | Finish Date | Duration
In foundation and basement upto 3 MT height
Inner wall
1st lift
Reinforcement | 2019-05-17 | 2019-05-18 | 2
Shuttering | 2019-05-19 | 2019-05-23 | 5
Concrete | 2019-05-24 | 2019-05-24 | 1
Puddle pipe - 2 Nos | 2019-05-24 | 2019-05-24 | 1
2nd lift
Reinforcement | 2019-05-25 | 2019-05-27 | 2
Shuttering & scaffolding | 2019-05-29 | 2019-06-01 | 4
Concrete | 2019-06-03 | 2019-06-03 | 1
3rd lift
Reinforcement | 2019-06-04 | 2019-06-06 | 2
Shuttering | 2019-06-07 | 2019-06-11 | 4
Concrete | 2019-06-12 | 2019-06-12 | 1
4th lift
Reinforcement | 2019-06-14 | 2019-06-15 | 2
Shuttering | 2019-06-17 | 2019-06-21 | 4 | 2019-06-24 | 2019-06-25 | 2
Concrete | 2019-06-22 | 2019-06-22 | 1 | 2019-06-26 | 2019-06-26 | 1 | -4
Walking Platform
Reinforcement | 2019-06-24 | 2019-06-25 | 2 | 2019-06-27 | 2019-06-28 | 2
Shuttering | 2019-06-26 | 2019-06-29 | 4 | 2019-06-29 | 2019-07-02 | 4
Concrete | 2019-07-01 | 2019-07-01 | 1 | 2019-07-03 | 2019-07-03 | 1 | -2
Outer wall
1st lift
Reinforcement | 2019-07-02 | 2019-07-03 | 2 | 2019-07-04 | 2019-07-05 | 2
Shuttering | 2019-07-05 | 2019-07-10 | 5 | 2019-07-06 | 2019-07-11 | 5
Concrete | 2019-07-12 | 2019-07-12 | 1 | 2019-07-12 | 2019-07-12 | 1 | 0
2nd lift
Reinforcement | 2019-07-13 | 2019-07-15 | 2
Shuttering | 2019-07-16 | 2019-07-20 | 5
Concrete | 2019-07-22 | 2019-07-22 | 1
3rd lift
Reinforcement | 2019-07-23 | 2019-07-24 | 2
Shuttering | 2019-07-25 | 2019-07-30 | 5
Concrete | 2019-07-31 | 2019-07-31 | 1
4th lift
Reinforcement | 2019-08-01 | 2019-08-03 | 2
Shuttering | 2019-08-05 | 2019-08-09 | 5
Concrete | 2019-08-10 | 2019-08-10 | 1
Ring beam
Reinforcement | 2019-08-02 | 2019-08-03 | 2
Shuttering | 2019-08-05 | 2019-08-10 | 5
Concrete | 2019-08-12 | 2019-08-12 | 1
Puddle Flange - 3 Nos | 2019-08-12 | 2019-08-12 | 1
Dome Slab
Shuttering | 2019-08-13 | 2019-08-24 | 10
Reinforcement | 2019-08-26 | 2019-09-01 | 6
Concrete | 2019-09-02 | 2019-09-02 | 1
Puddle pipe - 10 Nos | 2019-09-02 | 2019-09-02 | 1
Vent pipe | 2019-09-02 | 2019-09-02 | 1
Rubble stone Pitching | 2019-09-04 | 2019-09-05 | 2
Plinth protection slab | 2019-09-06 | 2019-09-06 | 1
Water proofing | 2019-09-16 | 2019-09-28 | 12
M.S.hand railing | 2019-09-04 | 2019-09-07 | 4
Inner & Outer Ladder Fabrication & erection | 2019-09-16 | 2019-09-26 | 10
Plastering
Outer Ring wall | 2019-09-17 | 2019-09-24 | 7
IPS flooring | 2019-09-03 | 2019-09-06 | 4
Painting
External | 2019-09-26 | 2019-10-01 | 6
Insert plate with painting | 2019-08-05 | 2019-08-05
Butterfly valve
DI pipe ( Pipe supplied by client)
Man hole cover
Rungs
Formulas:
Finish Date = [Start Date]+[Duration]-1
Finish Date = [Start Date]+[Duration]-1+1
Start Date = [Finish Date, row above]+1
Start Date = [Start Date, row above]

## Catchup schedule ELSR
Description | Finish Date
ELSR - 210 cum ( 210000 litre) | 2019-12-14
Outer Dia - 13.556 mtr
Total Height - 23.57 mtr
ELSR | AS PER SCHEDULE |  |  | CATCH-UP SCHEDULE
| START DATE | FINISH DATE | Duration | START DATE | FINISH DATE | Duration
3rd lift
Shuttering & scaffolding | 2019-05-17 | 2019-05-21 | 5 | Completed |  |  | 9
Concrete | 2019-05-22 | 2019-05-22 | 1
Filling with Gravel (inner) | 2019-05-23 | 2019-05-24 | 2
Inner PCC | 2019-05-25 | 2019-05-25 | 1
4th lift
scaffolding | 2019-05-27 | 2019-05-27 | 1 |  |  |  | 5
Reinforcement | 2019-05-27 | 2019-05-27 | 1
Shuttering | 2019-05-29 | 2019-05-30 | 2
Concrete | 2019-05-31 | 2019-05-31 | 1
5th lift
Reinforcement | 2019-06-01 | 2019-06-01 | 1 |  |  |  | 4
Shuttering & scaffolding | 2019-06-03 | 2019-06-04 | 2
Concrete | 2019-06-06 | 2019-06-06 | 1
6th lift
Reinforcement | 2019-06-07 | 2019-06-07 | 1 |  |  |  | 5
Shuttering & scaffolding | 2019-06-08 | 2019-06-11 | 3 | 2019-06-24 | 2019-06-25 | 2 |  | -14
Concrete | 2019-06-12 | 2019-06-12 | 1 | 2019-06-26 | 2019-06-26 | 1 |  | -14
7th lift
Reinforcement | 2019-06-14 | 2019-06-14 | 1 | 2019-06-27 | 2019-06-27 | 1 | 5
Shuttering & scaffolding | 2019-06-15 | 2019-06-18 | 3 | 2019-06-28 | 2019-06-29 | 2
Concrete | 2019-06-19 | 2019-06-19 | 1 | 2019-06-30 | 2019-06-30 | 1 |  | -11
8th lift
Reinforcement | 2019-06-20 | 2019-06-20 | 1 | 2019-07-01 | 2019-07-01 | 1 | 5
Shuttering & scaffolding | 2019-06-21 | 2019-06-24 | 3 | 2019-07-02 | 2019-07-03 | 2
Concrete | 2019-06-25 | 2019-06-25 | 1 | 2019-07-04 | 2019-07-04 | 1 |  | -9
9th lift
Reinforcement | 2019-06-26 | 2019-06-26 | 1 | 2019-07-05 | 2019-07-05 | 1 | 5
Shuttering & scaffolding | 2019-06-27 | 2019-06-29 | 3 | 2019-07-06 | 2019-07-07 | 2
Concrete | 2019-07-01 | 2019-07-01 | 1 | 2019-07-08 | 2019-07-08 | 1 |  | -7
10th lift
Reinforcement | 2019-07-02 | 2019-07-02 | 1 | 2019-07-09 | 2019-07-09 | 1 | 5
Shuttering & scaffolding | 2019-07-03 | 2019-07-05 | 3 | 2019-07-10 | 2019-07-11 | 2
Concrete | 2019-07-06 | 2019-07-06 | 1 | 2019-07-12 | 2019-07-12 | 1 |  | -6
11th lift
Reinforcement | 2019-07-08 | 2019-07-09 | 2 | 2019-07-13 | 2019-07-14 | 2 | 7
Shuttering & scaffolding | 2019-07-10 | 2019-07-13 | 4 | 2019-07-15 | 2019-07-17 | 3
Concrete | 2019-07-15 | 2019-07-15 | 1 | 2019-07-18 | 2019-07-18 | 1 |  | -3
12th lift
Reinforcement | 2019-07-16 | 2019-07-17 | 2 | 2019-07-19 | 2019-07-20 | 2 | 7
Shuttering & scaffolding | 2019-07-18 | 2019-07-22 | 4 | 2019-07-21 | 2019-07-23 | 3
Concrete | 2019-07-23 | 2019-07-23 | 1 | 2019-07-24 | 2019-07-24 | 1 |  | -1
13th lift
Reinforcement | 2019-07-24 | 2019-07-25 | 2 | 2019-07-25 | 2019-07-26 | 2 | 7
Shuttering & scaffolding | 2019-07-26 | 2019-07-30 | 4 | 2019-07-27 | 2019-07-30 | 4
Concrete | 2019-07-31 | 2019-07-31 | 1 | 2019-07-31 | 2019-07-31 | 1 |  | 0
14th lift
Reinforcement | 2019-08-01 | 2019-08-02 | 2 |  |  |  | 7
Shuttering & scaffolding | 2019-08-03 | 2019-08-06 | 4
Concrete | 2019-08-07 | 2019-08-07 | 1
15th lift
Reinforcement | 2019-08-08 | 2019-08-09 | 2 |  |  |  | 7
Shuttering & scaffolding | 2019-08-11 | 2019-08-15 | 4
Concrete | 2019-08-16 | 2019-08-16 | 1
16th lift
Reinforcement | 2019-08-17 | 2019-08-18 | 2 |  |  |  | 7
Shuttering & scaffolding | 2019-08-19 | 2019-08-22 | 4
Concrete | 2019-08-23 | 2019-08-23 | 1
Ring Beam
Reinforcement | 2019-08-24 | 2019-08-24 | 1 |  |  |  | 5
Shuttering & scaffolding | 2019-08-25 | 2019-08-27 | 3
Concrete | 2019-08-28 | 2019-08-28 | 1
Tank
Slab
Outer Compaction & PCC | 2019-07-08 | 2019-07-09 | 2
scaffolding | 2019-07-12 | 2019-08-30 | 50
Shuttering inc. staircase | 2019-08-31 | 2019-09-11 | 10 |  |  |  | 18
Reinforcement inc. staircase | 2019-09-13 | 2019-09-19 | 7
Concrete inc. staircase | 2019-09-20 | 2019-09-20 | 1
Haunch Ring Beam
Reinforcement | 2019-09-22 | 2019-09-23 | 2 |  |  |  | 5
Shuttering | 2019-09-25 | 2019-09-26 | 2
Concrete | 2019-09-28 | 2019-09-28 | 1
Shaft
Wall Starter | 2019-09-22 | 2019-09-22 | 1
1st lift 1.2mtr
Reinforcement | 2019-09-23 | 2019-09-24 | 2 |  |  |  | 5
Shuttering | 2019-09-25 | 2019-09-26 | 2
Concrete | 2019-09-27 | 2019-09-27 | 1
2nd lift
Reinforcement | 2019-09-28 | 2019-09-29 | 2 |  |  |  | 5
Shuttering | 2019-09-30 | 2019-10-01 | 2
Concrete | 2019-10-02 | 2019-10-02 | 1
3rd lift
Reinforcement | 2019-10-03 | 2019-10-04 | 2 |  |  |  | 5
Shuttering | 2019-10-05 | 2019-10-06 | 2
Concrete | 2019-10-07 | 2019-10-07 | 1
Cover Slab
Shuttering | 2019-09-28 | 2019-10-18 | 20 |  |  |  | 28
Reinforcement | 2019-10-19 | 2019-10-25 | 7
Concrete | 2019-10-26 | 2019-10-26 | 1
Deshuttering | 2019-10-26 | 2019-11-08 | 14
Head Room
Starter | 2019-10-27 | 2019-10-27 | 1
1st lift
Reinforcement | 2019-10-28 | 2019-10-28 | 1 |  |  |  | 3
Shuttering | 2019-10-29 | 2019-10-29 | 1
Concrete | 2019-10-31 | 2019-10-31 | 1
2nd lift
Reinforcement | 2019-11-01 | 2019-11-01 | 1 |  |  |  | 3
Shuttering | 2019-11-02 | 2019-11-02 | 1
Concrete | 2019-11-03 | 2019-11-03 | 1
Cover Slab
Shuttering | 2019-11-04 | 2019-11-05 | 2 |  |  |  | 4
Reinforcement | 2019-11-07 | 2019-11-07 | 1
Concrete | 2019-11-08 | 2019-11-08 | 1
RCC Parapet Wall -0.15x0.952
Shuttering | 2019-10-27 | 2019-10-29 | 3 |  |  |  | 6
Reinforcement | 2019-10-30 | 2019-10-31 | 2
Concrete | 2019-11-01 | 2019-11-01 | 1
water proofing treatment to vertical and horizontal surfaces | 2019-11-09 | 2019-11-10 | 2
Flooring | 2019-11-11 | 2019-11-11 | 1
Structural Staircase | 2019-11-09 | 2019-11-28 | 20
Shaft Ladder | 2019-11-29 | 2019-12-08 | 10
Hand Rail
Parapet Wall | 2019-11-08 | 2019-11-14 | 7
Head Room | 2019-11-15 | 2019-11-16 | 2
steel door | 2019-12-09 | 2019-12-10 | 2
Painting of steel doors & windows | 2019-12-11 | 2019-12-12 | 2
Ventilator | 2019-12-09 | 2019-12-11 | 2
Painting
Exterior - 1 coat primer,2 coats paint | 2019-12-09 | 2019-12-14 | 6
Interior - 1 coat primer,2 coats paint | 2019-12-09 | 2019-12-14 | 6
C.I manhole cover with frame | 2019-12-12 | 2019-12-12 | 1
Rubble stone Pitching
Plinth protection slab
Step
Service passage
Lightening Arrestor
Vent Pipe
Rain water drain pipe
200mm dia. Puddle flange | 2019-09-28 | 2019-09-28 | 1
300mm dia. Puddle flange | 2019-09-28 | 2019-09-28 | 1
Rungs
Formulas:
FINISH DATE = [AS PER SCHEDULE]+[Duration]-1
FINISH DATE = [AS PER SCHEDULE]+[Duration]-1+1
AS PER SCHEDULE = [FINISH DATE, row above]+1
AS PER SCHEDULE = [FINISH DATE, row above]
CATCH-UP SCHEDULE = [FINISH DATE, row above]+1

## Catchup Schedule Pump house
Description | Finish Date
Potable Pump House | 2019-10-05
Size of building - 9.17 x 16.37 mtr
Area of building - 150.11 sqm
Height of the building - 0.75+5.5+0.9
No. of Columns - 12
| AS PER SCHEDULE |  |  |  | CATCH - UP SCHEDULE
Pump Houses | Start Date | Finish Date | Duration | Actual status | Start Date | Finish Date
Column FGL to Beam bottom level
1st lift - 12 Columns |  |  |  |  | Completed
Shuttering | 2019-05-20 | 2019-05-21 | 2
Concrete | 2019-05-22 | 2019-05-22 | 1
2nd lift - 6 Columns |  | `
Reinforcement | 2019-05-23 | 2019-05-24 | 2
Shuttering | 2019-05-25 | 2019-05-25 | 1
Concrete | 2019-05-25 | 2019-05-25 | 1
2nd lift - 3 Bracket Columns |  |  | 1
Reinforcement | 2019-05-27 | 2019-05-27 | 1
Shuttering | 2019-05-28 | 2019-05-29 | 2
Concrete | 2019-05-30 | 2019-05-30 | 1
2nd lift - 3 Bracket Columns
Reinforcement | 2019-05-27 | 2019-05-27 | 1
Shuttering | 2019-06-06 | 2019-06-06 | 1
Concrete | 2019-06-07 | 2019-06-07 | 1
2nd lift - 6 Columns
Reinforcement | 2019-06-08 | 2019-06-08 | 1
Shuttering | 2019-06-09 | 2019-06-10 | 2
Concrete | 2019-06-11 | 2019-06-11 | 1
Roof Beam & slab
Outer Scaffolding | 2019-06-12 | 2019-06-19 | 8 |  | Completed
Shuttering | 2019-06-20 | 2019-06-25 | 6 | Material not received | 2019-06-20 | 2019-06-28
Reinforcement | 2019-06-26 | 2019-06-30 | 5 |  | 2019-06-29 | 2019-07-02 | 4
Concrete | 2019-07-01 | 2019-07-01 | 1 |  | 2019-07-03 | 2019-07-03 | 1
Deshuttering | 2019-07-16 | 2019-07-16 | 1 |  | 2019-07-18 | 2019-07-18 | 1
fly ash brick work
Upto Lintel | 2019-07-17 | 2019-07-23 | 7 |  | 2019-07-19 | 2019-07-24 | 6
Lintel & sun shade
Shuttering | 2019-07-24 | 2019-07-28 | 5 |  | 2019-07-25 | 2019-07-28 | 4
Reinforcement | 2019-07-29 | 2019-07-30 | 2
Concrete | 2019-07-31 | 2019-07-31 | 1
fly ash brick work
Above Lintel | 2019-08-02 | 2019-08-05 | 4
Ceiling Plastering | 2019-08-06 | 2019-08-09 | 4
Internal plastering | 2019-08-11 | 2019-08-16 | 6
Column above roof level
Reinforcement | 2019-07-02 | 2019-07-02 | 1
Shuttering | 2019-07-03 | 2019-07-03 | 1
Concrete | 2019-07-04 | 2019-07-04 | 1
fly ash brick work
Parapet wall | 2019-07-07 | 2019-07-08 | 2
External plastering | 2019-07-09 | 2019-07-16 | 8
Band | 2019-07-21 | 2019-07-26 | 6
Ramp | 2019-07-19 | 2019-07-23 | 5
Main entrance staircase & steps | 2019-07-25 | 2019-07-28 | 4
Anti termite treatment | 2019-07-30 | 2019-07-30 | 1
Weathering course | 2019-08-09 | 2019-08-11 | 3
tile | 2019-08-14 | 2019-08-16 | 3
Painting
External
1 coat primer | 2019-08-18 | 2019-08-19 | 2
2 coats of paint | 2019-08-21 | 2019-08-24 | 4
Ceiling
1 coat primer | 2019-08-28 | 2019-08-30 | 3
2 coats of paint | 2019-08-31 | 2019-09-04 | 5
Screed | 2019-08-18 | 2019-08-19 | 2
Internal Painting
1 coat primer | 2019-09-05 | 2019-09-06 | 2
2 coats of paint | 2019-09-07 | 2019-09-12 | 6
Painting in Steel | 2019-09-13 | 2019-09-15 | 3
Steel Doors Fixing | 2019-09-18 | 2019-09-18 | 1
aluminium glazed sliding window | 2019-09-20 | 2019-09-21 | 2
Mild steel grills | 2019-09-22 | 2019-09-22 | 1
rolling shutter | 2019-09-23 | 2019-09-26 | 4
Rain water pipe | 2019-09-28 | 2019-10-02 | 5
Rain water harvesting System | 2019-10-01 | 2019-10-05 | 5
Lightning arrestors and aviation lamp
conventional lightning air termination
G.I earth pipe
conductor using 25 mm X 6 mm G.I strip
LED type aviation lamp
Formulas:
Finish Date = [Start Date]+1
Finish Date = [Start Date]
Start Date = [Finish Date, row above]+1
Start Date = [Finish Date, row above]